## Requirements
Initial Delivery Phase | [8 empty] | Check Phase |  |  |  | Approval
Seq # | Req. ID | Requirement | Requirement (EN) | Package | % Completion | Effort | Checkpoint | Delivery Status | # Errors found | # Errors solved | % Errors solved | Check Status | Date | % ready | Delivery Status | Check Status
1 | BR-001 | Eliminación de Registros Fallidos (Cronjob) | Remove failed registrations (cronjob) | 1 | 0% | 1 | 2012-11-09 | In Progress | 0 | 0 | 100% | Not started |  | 0% | Not started | Not started
2 | UC-001 | Registro De Usuarios | Register user | 1 | 100% | 1 | 2012-11-09 | Delivered | 4 | 0 | 0% | Checked |  | 20% | In Progress | In Progress
3 | UC-002 | Confirmar Contraseña | Confirm registration | 1 | 100% | 1 | 2012-11-09 | Delivered | 1 | 0 | 0% | Checked |  | 40% | Delivered | Checked
4 | UC-003 | User Login | Login user | 1 | 100% | 1 | 2012-11-09 | Delivered | 3 | 0 | 0% | Checked |  | 60%
5 | UC-004 | Recuperar Contraseña | Recover password | 1 | 100% | 1 | 2012-11-09 | Delivered | 4 | 0 | 0% | Checked |  | 80%
6 | UC-005 | Mostrar Perfil | Display user profile | 1 | 100% | 1 | 2012-11-09 | Delivered | 1 | 0 | 0% | Checked |  | 100%
7 | UC-006 | Editar Perfil | Edit user profile | 1 | 80% | 1 | 2012-11-09 | In Progress | 2 | 0 | 0% | In Progress
8 | UC-007 | Cambiar Contraseña | Change password | 1 | 100% | 1 | 2012-11-09 | Delivered | 0 | 0 | 100% | Checked
9 | UC-009 | Editar Tags | Edit tags for profile | 1 | 100% | 1 | 2012-11-09 | Delivered | 1 | 0 | 0% | Checked
10 | UC-010 | Crear Curso | Create course | 1 | 100% | 1 | 2012-11-09 | Delivered | 6 | 0 | 0% | Checked
11 | UC-011 | Duplicar Curso | Duplicate course | 1 | 100% | 1 | 2012-11-09 | Delivered | 2 | 0 | 0% | Checked
12 | UC-012 | Borrar Curso | Delete course | 1 | 100% | 1 | 2012-11-09 | Delivered | 0 | 0 | 100% | Checked
13 | UC-013 | Editar Curso | Edit course | 1 | 80% | 1 | 2012-11-09 | In Progress | 0 | 0 | 100% | In Progress
14 | UC-014 | Añadir Tag a Curso | Add tag to a course | 1 | 100% | 1 | 2012-11-09 | Delivered | 0 | 0 | 100% | Checked
15 | UC-015 | Recomendar Curso | Recommend course | 1 | 0% | 2 | 2012-11-09 | In Progress | 0 | 0 | 100% | Not started
16 | UC-016 | Registrarse a Curso | Register a course | 1 | 100% | 3 | 2012-11-09 | Delivered | 1 | 0 | 0% | In Progress
17 | UC-017 | Comentar Curso | Comment a course | 1 | 20% | 2 | 2012-11-09 | In Progress | 0 | 0 | 100% | Not started
19 | UC-019 | Buscar Curso | Search course | 1 | 20% | 3 | 2012-11-09 | In Progress | 0 | 0 | 100% | Not started
20 | UC-020 | Buscar a Expertos | Search for experts | 1 |  | 4 |  | Not started | 0 | 0 | 100% | Not started
21 | UC-021 | Evaluar Curso | Evaluate course | 1 |  | 2 |  | Not started | 0 | 0 | 100% | Not started
22 | UC-022 | Cancelar Participación | Cancel course | 1 |  | 1 |  | Not started | 0 | 0 | 100% | Not started
30 | UC-035 | Gestión Electrónica de Documentos | Adminstrate course media | 1 |  | 4 |  | Not started | 0 | 0 | 100% | Not started
31 | UC-036 | Administrar Participantes | Administrate participants | 1 |  | 4 |  | Not started | 0 | 0 | 100% | Not started
32 | UC-037 | Cronograma del Curso | Edit course cronogram | 1 |  | 4 |  | Not started | 0 | 0 | 100% | Not started
18 | UC-018 | Ingresar Aula Virtual | Attend course session | 2 |  | 2 |  | Not started | 0 | 0 | 100% | Not started
23 | UC-023 | Salir del aula virtual | Leave course session | 2 |  | 1 |  | Not started | 0 | 0 | 100% | Not started
24 | UC-024 | Editar las condiciones generales del contrato | Edit course terms and conditions | 2 |  | 3 |  | Not started | 0 | 0 | 100% | Not started
25 | UC-025 | Creación de Tests | Create tests | 2 |  | 6 |  | Not started | 0 | 0 | 100% | Not started
26 | UC-026 | Participar en Test | Attend a test | 2 |  | 3 |  | Not started | 0 | 0 | 100% | Not started
27 | UC-027 | Observar Curso | Follow course | 2 |  | 4 |  | Not started | 0 | 0 | 100% | Not started
28 | UC-028 | Proponer Curso | Suggest a course | 2 | 60% | 4 |  | In Progress | 0 | 0 | 100% | Not started
29 | UC-029 | Buscar Cursos Propuestos | Search suggested courses | 2 |  | 4 |  | Not started | 0 | 0 | 100% | Not started
33 | UC-038 | Comentarios Área Cerrada | Process comments in locked area | 2 |  | 4 |  | Not started | 0 | 0 | 100% | Not started
34 | UC-039 | Implementar OpenChat | OpenChat implementation | 2 |  | 4 |  | Not started | 0 | 0 | 100% | Not started

## Errors
Seq-Nr. | Req-ID | Requirement | Error ID | Error Description | Criticality | Issue Date | Solve Date | Status | error_type | error_status
1 | UC-003 | Login user | E-001 | Login requires clicking on "Login" | low | 2012-11-11 |  | Identified | high | Identified
2 | UC-003 | Login user | E-002 | Firefox is not asking to save username and password. Why? Usually he asks on every form. He should do that! What are the technical issues preventing that? | low | 2012-11-11 |  | Identified | medium | In Progress
3 | UC-002 | Confirm registration | E-003 | E-003: Text of registration email: “Please Confirm Registration” “ … - Do not reply to this message!” “To continue registration process, please confirm your account by clicking here” | low | 2012-11-11 |  | Identified | low | Solved
4 | UC-001 | Register user | E-004 | E-004: Layout of registration email: Please according to corporate design | low | 2012-11-11 |  | Identified
5 | UC-005 | Display user profile | E-005 | E-005: Email not looking nice. There should be no line break on email-addresses like this. | low | 2012-11-11 |  | Identified
6 | UC-006 | Edit user profile | E-006 | E-006: Changes should be saved automatically when leaving form (not only explicitly by clicking the “save” button) | medium | 2012-11-11 |  | Identified
7 | UC-006 | Edit user profile | E-007 | E-007: Edit your photo not working nothing happens | high | 2012-11-11 |  | Identified
8 | UC-004 | Recover password | E-008 | E-008: Nothing happens after clicking on “send” | high | 2012-11-11 |  | Identified
9 | UC-009 | Edit tags for profile | E-009 | E-009: Do not replace upper case letters (e.g. “IT”) by lower case letters (e.g. “it”). Only treat them internally as identical | low | 2012-11-11 |  | Identified
10 | UC-016 | Register a course | E-010 | E-010: Not able to open course via search to register. | high | 2012-11-11 |  | Identified
11 | UC-010 | Create course | E-011 | E-011: Price: There should be a currency displayed (e.g. Euro) | high | 2012-11-11 |  | Identified
12 | UC-010 | Create course | E-012 | E-012: Part. Number: Min or Max? Maybe both? | high | 2012-11-11 |  | Identified
13 | UC-010 | Create course | E-013 | E-013: There should be selection of course type: “podcast” or “regular course” Podcast only requires: title, description, price, video upload, image, duration (automatically filled after video upload), tags | high | 2012-11-11 |  | Identified
14 | UC-010 | Create course | E-014 | E-014: Certificate? What for? Remove! | medium | 2012-11-11 |  | Identified
15 | UC-010 | Create course | E-015 | E-015: Dates: Start date can be removed. Dates should be entered one by one (incl. time and timezone!!) after entering one date there should be a “add additional date” line and/or button | high | 2012-11-11 |  | Identified
16 | UC-010 | Create course | E-016 | E-016: Duration: Can then be calculated automatically. Please additionally display “number of events” which can also be automatically calculated | high | 2012-11-11 |  | Identified
17 | UC-011 | Duplicate course | E-017 | E-017: Error message should display what was wrong saving the copy and not just saying that it was wrong. | medium | 2012-11-12 |  | Identified
18 | UC-011 | Duplicate course | E-018 | E-018: Is it possible to have here some kind of breadcrumb navigation? For more user-friendly navigation by getting to the erroneous fields. This should be configured on the top of the formular. | low | 2012-11-12 |  | Identified
19 | UC-003 | Login user | E-019 | E-019: Misspelling not “Sig up” but “Sign up” | low | 2012-11-18 |  | Identified
20 | UC-001 | Register user | E-020 | E-020: When signing up with a taken account, the remarks are not looking nice regarding line-break and span | low | 2012-11-18 |  | Identified
21 | UC-004 | Recover password | E-021 | E-021: When clicking on "send" the progress bar occurs and an email is sent. But even after receiving the email the progress bar still shows action. A message like "the email is now sent" or similar should be displayed to the user on the web frontend. | medium | 2012-11-18 |  | Identified
22 | UC-004 | Recover password | E-022 | E-022: After receiving email to confirm password reset the plain login page is displayed. There should be some kind of comment, that there is an email send with the new password. | medium | 2012-11-18 |  | Identified
23 | UC-001 | Register user | E-023 | E-023: Please no editable field after clicking on "register". Fields should change into non-editable labels. | medium | 2012-11-18 |  | Identified
24 | UC-001 | Register user | E-024 | E-024: After clicking "send" the "send" button should be removed or greyed out / non-clickable. | medium | 2012-11-18 |  | Identified
21 | UC-004 | Recover password | E-025 | E-025: If Email could not be sent (e.g. due to email-server not available) , please show appropriate error message instead of ongoing progress bar. | medium | 2012-11-18 |  | Identified
test